## Gantt Chart
GANTT CHART SD2 - CHATBOT
PROJECT TITLE: |  | Weather Chatbot |  |  |  |  | Software Development 2
PROJECT MEMBERS: | [6 empty] | LAB MEETING | [6 empty] | MONDAYS: 10:30-11:00 AM
Karen Magalhaes-3146094 ¦ Thales Campos-3151261 ¦ Vitor Freitas-3152612
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | TASK COMPLETE | Milestone 01 | [14 empty] | Milestone 02 | [13 empty] | Milestone 03
[7 empty] | WEEK 7 | [7 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13
[7 empty] | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
[7 empty] | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
1 | Project Conception - basic design and functionalities
1.1 | Trello | Thales | 2025-03-03 | 2025-03-10 | 3 | 100% | bar: WEEK 7 S 9 to WEEK 7 T 11
1.2 | Wireframes | Thales | 2025-03-03 | 2025-03-10 | 1 | 100% | bar: WEEK 7 S 9
1.3 | Logo | Thales | 2025-03-03 | 2025-03-10 | 1 | 100% | bar: WEEK 7 S 9
1.4 | Requirements | Vitor | 2025-03-03 | 2025-03-10 | 2 | 100% | bar: WEEK 7 S 9
1.5 | Github Repository | Vitor | 2025-03-03 | 2025-03-10 | 1 | 100% | bar: WEEK 7 S 9
1.6 | Research | Karen | 2025-03-03 | 2025-03-10 | 3 | 50% | bar: WEEK 7 S 9 to WEEK 7 T 11
1.7 | Flows and Chart | Karen | 2025-03-03 | 2025-03-10 | 3 | 60% | bar: WEEK 7 S 9; WEEK 8 T 18 to WEEK 8 W 19
1.8 | Prototype | Vitor | 2025-03-10 | 2025-03-16 | 7 | 100% | bar: WEEK 7 M 10 to WEEK 7 S 16
1.8.2 | Coding - tests | Thales | 2025-03-10 | 2025-03-16 | 3 | 0% | bar: WEEK 8 M 17 to WEEK 8 W 19
1.8.2 | Coding - tests | Karen | 2025-03-10 | 2025-03-16 | 3 | 0% | bar: WEEK 8 M 17 to WEEK 8 W 19
1.8.2 | Coding - tests | Vitor | 2025-03-10 | 2025-03-16 | 3 | 0% | bar: WEEK 8 M 17 to WEEK 8 W 19
1.8.2 | - | - | - | - | - | 0%
1.9 | Define audience | Thales | 2025-03-16 | 2025-03-23 | 1 | 100% | bar: WEEK 7 S 9
1.11 | Define persona | Karen | 2025-03-16 | 2025-03-23 | 2 | 0% | bar: WEEK 7 M 10 to WEEK 7 T 11
1.11 | Map edge cases | Thales | 2025-03-16 | 2025-03-23 | 1 | 0% | bar: WEEK 7 T 11
1.12 | Entity mapping | Thales | 2025-03-16 | 2025-03-23 | 1 | 0% | bar: WEEK 7 T 11
1.12 | Onboarding | Group | 2025-03-16 | 2025-03-23 | 1 | 0% | bar: WEEK 7 T 11
- | - | - | - | - | - | 0%
- | - | - | - | - | - | 0%
2 | Project Production - Functionalities for most of the app features
2.1 | - | - | - | - | 0 | 0% | bar: WEEK 9 M 24 to WEEK 9 S 30
| - | - |  |  | 0 | 0%
| - | - |  |  | 0 | 0%
| - | - |  |  | 0 | 0%
3 | Project Conclusion - App fully functioning
| - | - |  |  | 0 | 0%
| - | - |  |  | 0 | 0%
| - | - |  |  | 0 | 0%
| - | - |  |  | 0 | 0%
| - | - |  |  | 0 | 0%
| - | - |  |  | 0 | 0%
4 | Project Performance / Monitoring
4.1 | Project Final Documentation | Group | 2025-03-10 | 2025-04-27 | 50 | 0%
| - | - |  |  | 0 | 0%
| - | - |  |  | 0 | 0%
| - | - |  |  | 0 | 0%
Note on I8: The basic design and functionalities of your app should be demonstrated. You need to submit: • An archive of your project so far including the git repository (only zip format is accepted). • Your project documentation. (only pdf or .docx format is accepted). • A 1-page report detailing what changes have been made since the previous review.
Note on X8: Functionalities should be demonstrated for most of the app features. You need to submit: • An archive of your project including the git repository (only zip format is accepted). • Your project documentation. (only pdf or .docx format is accepted). • A 1-page report detailing what changes have been made since the previous review.
Note on AL8: Your app should be fully functioning. You will need to submit: • Archive of your complete project including a link to the git repository (only zip format is accepted). • The full project documentation (only pdf or .docx format is accepted). • A 1-page report detailing what changes have been made since the previous review.